## Slide 1
GOVERNMENT OF THE DISTRICT OF COLUMBIA
Department of Behavioral Health and Department of Health Care Finance
Behavioral Health Integration Stakeholder Advisory Group Meeting Agenda
December 8, 2021
4:00-5:00 pm
Welcome Angele Moss-Baker, DBH
Overview of Work Group Recommendations Melisa Byrd, DHCF
and Government Decision-Making Dr. Barbara J Bazron, DBH
Public Comment Members of the Public
Next Steps Melisa Byrd, DHCF
Dr. Barbara J. Bazron, DBH
Adjournment Angele Moss-Baker, DBH

## Slide 2
Behavioral Health Integration
Project Work To-Date
Stakeholder Advisory Group Meeting​
December 8, 2021​

## Slide 3
Behavioral Health Integration – Project Organization
Work Stream 1:
New Medicaid Services
Leadership Team
(Dr. Barbara Bazron & Melisa Byrd)
Decision-making
Work Stream 2: MCO Contractual Considerations
Steering Committee
Project Monitoring and Input
Work Stream 3:
Stakeholder Support and Communications
Work Stream 4: Performance Metrics and Population Monitoring
Work Stream 5: Provider Rate-Setting
3
Work Group 1:
New Medicaid Services
SUBMITTED
Work Group 2: MCO Contractual Considerations
Work Group 3:
Stakeholder Support and Communications
Work Group 4: Performance Metrics and Population Monitoring
SUBMITTED
SUBMITTED
In Progress
SUBMITTED

## Slide 4
Decision-Making Process
Leadership Team
(Dr. Barbara J. Bazron and
Melisa Byrd)
Decision-making
Steering Committee
Project Monitoring and Input
Work Streams
Work Groups
Reviews and makes final decisions based on recommendations from Work Streams
Provides guidance and feedback on recommendations from Work Streams
Develops recommendations based on subject matter expertise and stakeholder feedback
Develops recommendations based on stakeholder expertise for integration into Work Stream recommendations and to be sent to Steering Committee/Leadership

## Slide 5
All work to-date has included a broad and diverse array of participation from Individuals with Lived Experience of the BH System, Advocates, Community Members, Provider Organizations, Managed Care Organizations, and Government Agency Staff. The Stakeholder Advisory Group meetings which are open to the Public, have been a large part of the efforts to include representation across stakeholder groups, and convened eight (8) times since publication of their Charter in March 2021.

## Slide 6: Thank You!

## Slide 7
Behavioral Health Integration
Key Decisions
Stakeholder Advisory Group Meeting​
December 8, 2021​

## Slide 8: New Implementation Date: OCTOBER 1, 2023
Allows for inclusion of the Managed Care Organizations in Readiness and Implementation activities.
Separated Behavioral Health Transformation from all other Transitions which must occur on October 1, 2022.
Generally, provides more time for Development, Planning, and Readiness

## Slide 9: Work Stream 1 – Work Group 1 (Services)
Work Stream 1/Work Group 1 provided recommendations to the Steering Committee, and subsequently the Directors of DBH and DHCF,
for Services, new and existing, for inclusion in the Rate Study.
Some of the recommendations include alternative payment models and some represent priorities for the District such as High-Fidelity Wraparound and Peer Support Services.

## Slide 10: Services
The proposed SERVICE ARRAY per the RFP, refers to the current DBH Rules. This allows the contract to be current as changes are made via regulation
All mental health benefits provided through the District of Columbia’s State Plan Amendment (SPA) and Medicaid Waiver(s) (as applicable) operationalized through the District of Columbia Municipal Regulations (DCMR) including, but not limited to the following:
22-A DCMR Chapter 30, Free Standing Mental Health Clinic Certification Standards;
22-A DCMR Chapter 34, Mental Health Rehabilitation Services Provider Certification Standards;
22-A DCMR Chapter 35, Child Choice Provider Certification;
22-A DCMR Chapter 36, Child Choice Providers – Specialized Services and Reimbursement Rates;
22-A DCMR Chapter 37, Mental Health and Substance Abuse Disorder Supported Employment Services and Provider Certification Standards;
22-A DCMR Chapter 39, Psychosocial Rehabilitation Clubhouse Certification Standards; and
22-A DCMR Chapter 80, Certification Standards for Behavioral Health Stabilization Providers.

## Slide 12: The District is striving for accessible, continuous, and effective whole person care across the Lifespan.
We are now requiring screening, referral, and connection to treatment for High Fidelity Wrap Around and Community Based Intervention services,
during the first 48 hours of any admission to an Acute Care Facility,
which will provide District Youth and Families experiencing needs for intensive services, with the opportunity to connect with the appropriate level of community-based care.

## Slide 13: Work Stream 2 – Work Group 2 (Contracting)
Work Stream 2/Work Group 2 provided recommendations to the Steering Committee and the Directors, under expedited timelines, to inform our interagency collaboration and development of the Request for Proposal (RFP), which will reprocure
the Managed Care contracts to include
the full complement of Behavioral Health Services in the District.

## Slide 14
DC Healthcare Alliance Program Participants will have FULL coverage for Mental Heath and Substance Use Disorder Assessment and Treatment

## Slide 15: Improving Health Plan Accountability for Behavioral Health
In the past, some Health Plans have separated their Case Management Departments
by Physical Health & Behavioral Health, through use of Subcontracted BHOs.
We are now requiring that Case Management Departments are Integrated.
Aligns with our goal of whole-person care
Shifts towards a more coordinated
(less fragmented), accountable,
and data-driven, system of care
Achieves Parity

## Slide 16: TRANSITION PLANNING
DBH and DHCF agree that continuity of care is critical to a successful BH Integration.
Continuity of Care Policies in development will allow Beneficiaries an additional 180-day authorization, at the conclusion of their current treatment plan, after October 1, 2023.

## Slide 17: Work Stream 3 - Work Group 3 (Stakeholders)
Work Stream 3/Work Group 3, with approval from the Steering Committee and the Directors, developed and administered Provider Organization Surveys and Forums,
to discover and understand the needs of Providers
for future Trainings and Technical Assistance related to
the BH Transition into Managed Care.

## Slide 18: Network Adequacy
DHCF and DBH strive to have
ALL DBH-certified Providers contracted with
at least one Managed Care Organization
by the Date of Implementation,
including a successful test claim.

## Slide 20: Work Stream 4 - Work Group 4 (Performance)
Work Stream 4/Work Group 4 are finalizing recommendations about how to communicate the Performance of the system of care to the broader DC community, and selecting the data reports, measures, and performance priorities that will Evaluate the initial years in Managed Care.

## Slide 21: Performance Metrics and Population Monitoring
The Medicaid Managed Care Annual Technical Report
will include the
FULL SET of CMS’s CORE MEASURES
for Mental Health and Substance Use Disorders.

## Slide 22: Work Stream 5 – Rate Study

## Slide 23
Notes: PCG to speak to this slide

## Slide 24
SAG Chairs & Members
Comment
Stakeholder Advisory Group Meeting
December 8, 2021

## Slide 25: What’s Next?

## Slide 26
November 2021 – December 2022: Planning and Development
Complete RATE STUDY
Develop Medicaid STATE PLANS and corresponding DHCF and DBH REGULATIONS for new/revised services
On-going Provider TRAINING and TECHNICAL ASSISTANCE
ARPA EHR/HIE initiative
Managed Care Organization solicitation, readiness, and implementation
DHCF-DBH MOU development
January 1, 2023 – September 30, 2023: Formal Readiness Period
Routine agency, provider, managed care plan collaboration
Providers are ACCREDITED and CERTIFIED
Provider and managed care plan CONTRACTING
Claims system TESTING
DATA sharing
Outreach and communication with BENEFICIARIES.
Stay tuned for A new BH Integration PROJECT PLAN and STRUCTURE,
which will include the Stakeholder Advisory Group & Meetings and continue to engage Community feedback in addition to Interagency Government participation.

## Slide 27
Public Comment
Stakeholder Advisory Group Meeting
December 8, 2021